## AABF Soccer Tasks (2007)
Category | Action Item | Responsible Party | Suspense Date | Status | Notes
Corporation | Renew AABF P.O. Box | Treasurer | 2007-01-27 | Open
Season Setup | Define Season Calendar and Assign Board Responsibilities | Board | 2007-03-06 | Open | Registration, Coaches Clinic, Players Clinic, Practice, Games, Soccer Festival
Season Setup | Inventory and Evaluate Equipment and determine whether we need to purchase any equipment | Board | 2007-03-06 | Open | First Aid Kit, Cones, Balls, Bags, Nets
Registration | Create Registration Form | Manzione | 2007-03-06 | Open
Season Setup | Define, present, and pick from Uniform (Referee, Player, Goalkeeper Penney) and Sock options | Thomas | 2007-03-06 | Open | Define logo and colors
Corporation | File Annual Report with CO SOS | Treasurer | 2007-03-31 | Open | Can file electronically at http://www.sos.state.co.us
Season Setup | Prepare Referee Application | Board | 2007-04-03 | Open
Corporation | Board Meeting | Board | 2007-04-03 | Open
Season Setup | Update Code of Conduct | Taylor | 2007-04-05 | Open
Season Setup | Update Rules | Taylor | 2007-04-05 | Open
Registration | Make copies of Registration Form | Taylor | 2007-04-05 | Open
Season Setup | Change AABF Voicemail message | Thomas | 2007-04-05 | Open
Season Setup | Interview and select Head Referee | Board | 2007-05-01 | Open
Corporation | Board Meeting | Board | 2007-05-01 | Open
Website | Post Registration Form on Website | Taylor | 2007-05-01 | Open
Season Setup | Publish articles in local newspapers |  | 2007-05-01 | Open
Registration | Registration Forms to Thursday Folders | Thomas | 2007-05-02 | Open
Season Setup | Organize Coaches Clinic | Manzione | 2007-05-03 | Open
Website | Post Referee Ad on Website | Taylor | 2007-05-03 | Open
Website | Post Code of Conduct on Website | Taylor | 2007-05-06 | Open
Website | Post Rules on Website | Taylor | 2007-05-06 | Open
Website | Post Season Schedule on Website | Taylor | 2007-05-06 | Open
Website | Update Board Members on Website | Taylor | 2007-05-06 | Open
Website | Update Calendar of Events on Website | Taylor | 2007-05-06 | Open
Season Setup | Order Shirts and Socks | Thomas | 2007-05-07 | Open | 2 weeks prior to coaches clinic
Season Setup | Organize Players Clinic | Manzione | 2007-05-10 | Open
Registration | Conduct Registration Night at EWE | Taylor | 2007-05-10 | Open | PTO Event
Season Setup | Recruit Coaches and Division Coordinators | All | 2007-05-11 | Open
Registration | Distribute Registration Form | All | 2007-05-11 | Open
Registration | Sort Registration Forms | All | 2007-05-30 | Open
Registration | Registration Data Entered into Database | All | 2007-05-30 | Open
Registration | Registration Deadline | N/A | 2007-05-30 | Open
Season Setup | Create Season Roster | All | 2007-06-01 | Open
Season Setup | Conduct Coaches Clinic | Manzione | 2007-06-02 | Open
Season Setup | Referee Training |  | 2007-06-02 | Open
Corporation | Board Meeting | Board | 2007-06-05 | Open
Season Setup | Conduct Players Clinic | Manzione | 2007-06-09 | Open
Season Setup | Distribute Shirts | Thomas | 2007-06-09 | Open | Distribute at Players Clinic
Season Setup | Open Practice Begins |  | 2007-06-11 | Open
Season Setup | Submit Insurance Form and Payment |  | 2007-06-14 | Open
Season Setup | Open Practice Ends |  | 2007-06-15 | Open
Season Setup | Specify Board Member coverage for each Game | Board | 2007-06-18 | Open
Season Setup | Season Opens |  | 2007-06-18 | Open
Corporation | Conduct Election for Vice Chairperson and Secretary | Secretary | 2007-06-29 | Open
Season End | Order Coaches Gifts |  | 2007-07-04 | Open
Season End | Order Awards for Players |  | 2007-07-04 | Open
Season End | Take Team Photos |  | 2007-07-20 | Open
Season End | Conduct End of Season Surveys |  | 2007-07-20 | Open
Season End | Season Ends |  | 2007-07-27 | Open
Season End | Soccer Festival |  | 2007-07-27 | Open
Corporation | Collect and Store Equipment |  | 2007-07-29 | Open
Corporation | Season Review Meeting | Board | 2007-08-07 | Open | Coaches
Season End | Provide End of Season Financials to Board | Treasurer | 2007-08-07 | Open
Website | Post Team Photos on Website | Taylor | 2007-08-12 | Open
Season End | Black Forest Parade |  | 2007-08-18 | Open
Corporation | Board Meeting | Board |  | Closed
Season Setup | Reserve fields in BF Regional Park | Manzione |  | Closed
Corporation | Annual Payment Due to Alpha Page Voicemail | Treasurer |  | Closed
Formulas:
Suspense Date = IF(EXACT([Status],"Open"),DATEVALUE("1/27/2007"),"")