## AABF Soccer Tasks (2012)
Category | Action Item | Responsible Party | Suspense Date | Status | Notes
Corporation | Annual Payment Due to Alpha Page Voicemail | Treasurer |  | Closed
Corporation | Board Meeting | Board |  | Closed | 6:30pm at Subway
Season Setup | Reserve fields in BF Regional Park | Bjornsrud/Conley |  | Closed
Season Setup | Define Season Calendar and Assign Board Responsibilities | Board |  | Closed | Registration, Coaches Clinic, Players Clinic, Practice, Games, Soccer Festival
Corporation | File Annual Report with CO SOS | Conley |  | Closed | Can file electronically at http://www.sos.state.co.us
Season Setup | Change AABF Voicemail message | Bjornsrud |  | Closed
Corporation | Board Meeting | Board |  | Closed | 6:30 Subway
Corporation | Renew AABF P.O. Box | Stevens |  | Closed | Shari and Brett to transfer Box obligations
Registration | Create Registration Form | Board |  | Closed | Final Board Approval
Season Setup | Prepare Referee Application | Board |  | Closed | Final Board Approval
Season Setup | Update Code of Conduct | Board |  | Closed | Final Board Approval
Season Setup | Update Rules | Board | 2012-04-12 | Open | Final Board Approval
Registration | Make copies of Registration Form | Conley |  | Closed
Website | Post Referee Ad on Website | Taylor |  | Closed
Season Setup | Publish articles in local newspapers | Trska |  | Closed
Website | Post Code of Conduct on Website | Taylor |  | Closed | Needs review regarding Coach/Parent expectations
Website | Post Rules on Website | Taylor | 2012-04-12 | Open
Website | Post Season Schedule on Website | Taylor |  | Closed
Website | Update Board Members on Website | Taylor |  | Closed | New Board Members:John Trcka, Jim & Andrea Nagy, Mike Lujan, and Pierre Gaudreault.
Website | Update Calendar of Events on Website | Taylor |  | Closed
Website | Post Registration Form on Website | Taylor |  | Closed
Registration | Distribute Registration Form | All |  | Closed
Corporation | Board Meeting | Board |  | Closed | Meeting Minutes to follow
Season Setup | Define, present, and pick from Uniform (Referee, Player, Goalkeeper Penney) and Sock options | Board |  | Closed | Define logo and colors
Corporation | Board Meeting | Board |  | Closed | Meeting Minutes to follow
Season Setup | Order Shirts and Socks | Vialpando |  | Closed | Minimum 3 weeks prior to coaches clinic.
Season Setup | Organize Coaches Clinic | Board | 2012-05-23 | Open
Corporation | Board Meeting | Board | 2012-05-23 | Open | Meeting Minutes to follow
Season Setup | Inventory and Evaluate Equipment and determine whether we need to purchase any equipment | Nagy | 2012-05-23 | Open | First Aid Kit, Cones, Balls, Bags, Nets, Goals
Season Setup | Organize Players Clinic | Board | 2012-05-23 | Open
Registration | Registration Deadline | N/A | 2012-05-31 | Open
Registration | Sort Registration Forms | All | 2012-06-01 | Open
Season Setup | Interview and select Head Referee | Gaudreault | 2012-06-01 | Open
Season Setup | Recruit Coaches and Division Coordinators | All | 2012-06-01 | Open | John Trcka
Registration | Registration Data Entered into Database | Stevens | 2012-06-03 | Open
Season Setup | Create Season Roster | All | 2012-06-03 | Open
Corporation | Board Meeting | Board | 2012-06-06 | Open | Meeting Minutes to follow
Season Setup | Conduct Coaches Clinic | All | 2012-06-09 | Open
Season Setup | Distribute Shirts |  | 2012-06-09 | Open | Distribute at Players Clinic
Season Setup | Conduct Players Clinic | All | 2012-06-09 | Open
Season Setup | Practice Begins | N/A | 2012-06-11 | Open
Season Setup | Submit Insurance Form and Payment | Lujan | 2012-06-11 | Open
Season Setup | Specify Board Member coverage for each Game | Board | 2012-06-11 | Open
Season Setup | Referee Training | Gaudreault | 2012-06-16 | Open
Corporation | Board Meeting | Board | 2012-06-20 | Open
Season Setup | Open Practice Ends | N/A | 2012-06-22 | Open
Season Setup | Season Opens | N/A | 2012-06-25 | Open
Corporation | Conduct Election for Chairperson, Vice Chairperson, Treasurer and Secretary | Secretary | 2012-06-29 | Open
Season End | Order Coaches Gifts | Stevens/Conley | 2012-07-06 | Open
Season End | Order Awards for Players | Stevens | 2012-07-06 | Open
Season End | Take Team Photos | Hilda Nic. | 2012-07-12 | Open
Season End | Conduct End of Season Surveys | Secretary | 2012-07-12 | Open
Season End | Season Ends | N/A | 2012-07-26 | Open
Season End | Soccer Festival | Board | 2012-07-27 | Open
Corporation | Collect and Store Equipment / Inventory and Evaluate Equipment | Nagy | 2012-07-27 | Open
Corporation | Season Review Meeting | Board | 2012-08-03 | Open | Coaches
Season End | Provide End of Season Financials to Board | Treasurer | 2012-08-03 | Open
Website | Post Team Photos on Website | Taylor | 2012-08-03 | Open
Season End | Black Forest Parade | Conley |  | Open
Formulas:
Suspense Date = IF(EXACT([Status],"Open"),DATEVALUE("4/12/2012"),"")